## Trainings
S.No | Training | SME Name | Material Readiness | Mode | Target Audience | Remarks | 20th Apr | 21st Apr | 22nd Apr | 23rd Apr | 24th Apr | 27th Apr | 28th apr | 29th Apr | 30th Apr | 1st May | 4th May | 5th May | 6th May | 7th May | 8th May
1 | Uitility Domain Introduction - A | NA | Yes | Self-Study | Both | Electric Distribution Operations PPT | 2 hr | [14 empty] | Self-Study | Yes | Dev
2 | Uitility Domain Introduction - B | Doug | Yes | Remote | Both | Electric Distribution Operations PPT | 2 hr | [14 empty] | Remote | No | QA
3 | DMS Product Overview and Software Architecture | Prashanth | Yes | Remote | Both |  | 3hr | [14 empty] | Face to Face |  | Both
4 | DMS Y 2015 work, Product Major Releases and Customers | Prashanth |  | Remote | Both |  | 1 hr
5 | DMS Demo | Leslie | Yes | Face to Face | Both |  |  | 1hr
6 | DMS Software Installation | Leslie/John M[Remote] | Yes | Face to Face | Both | SDDE image and installation document to be used |  | 4 hr
7 | Hands-On Exercises | Leslie/Doug[Remote] | Yes | Face to Face | Both | Run Smoke test plan |  | 2 hr
8 | Test and Explore the product | NA |  | Self-Study | Both | Run subset of Regression plan |  |  | 8 hr
9 | Code Management process and tool (TFS) hands-on | Leslie |  | Remote | Both | Cover the process and any specific do's and don't for using the TFS |  |  |  | 4 hr
10 | Build process and build system hands-on | Leslie |  | Remote | Both |  |  |  |  | 2 hr
12 | Testing Process | Jaya |  | Remote | Both | Test Case Creation Process Test Execution Process Defect Logging Process Defect Triage Process |  |  |  |  | 4 hr
13 | Buffer day for any spill overs | NA |  | Remote | Both | [6 empty] | 8 hr
14 | Design Walkthrough (Generic) | Leslie |  | Face to Face | Both | [7 empty] | 4 hr
15 | Testing case design & creation (High Level) | Jaya |  | Remote | Both | Sprint Version One Task Traceability Matrix Test Case Creation Test Case Review ALM Tool Version One Tool | [6 empty] | 4 hr
16 | Design Walkthrough and Code organisation (Module level) | Leslie/Multiple |  | Face to Face | Dev | Parrallel sessions as per team distribution across modules UI, server and TIBCO | [7 empty] | 4 hr
17 | Design Walkthrough (Functional Level) | Leslie/Multiple |  | Face to Face | Dev | Second day is remote | [7 empty] | 4 hr | 4 hr
18 | Testing case design & creation (Detailed) | Jaya |  | Remote | QA | Functional, Integration and End to End test cases creation and Walk through ALM Tool | [7 empty] | 4hr
19 | Buffer time for any spill overs | NA |  | Remote | Both | [9 empty] | 4 hr
20 | Code Walkthrough and Debuging technique (module level) | Leslie |  | Remote | Dev | [10 empty] | 8 hr | 8 hr | 8 hr
21 | Test case Execution Walkthrough, creation and execution | Jaya |  | Remote | QA | Test Case Execution in ALM | [9 empty] | 4 hr | 4 hr
22 | Training on Agile methodology (Version One tool understanding) | Leslie |  | Remote | Both | [13 empty] | 8 hr
23 | Pilot Sprint Planning for bug fixing Hands-On | NA |  | Remote | Both | [14 empty] | 8 hr | 8 hr
11 | Defect Management process and Clearquest hands-on | Doug/Jaya |  | Remote | Both | Defect Life Cycle Management - CQ and TFS CQ- Defect Management Tool TFS- Defect Management Tool |  |  |  |  | 4hr

## Sheet2
Self-Study
Web-Ex
In-Person